## Project tasks
Project name | JAKE DEDERT COACHING WEBSITE
Plan owner | Akhilesh Boda
Project start date | 2025-07-09 09:00
Project finish date | 2025-08-11 17:00
Duration | 34 days
% complete | 0%
Exported on | 2025-07-09 10:04
Task number | Outline number | Name | Assigned to | Start | Finish | Duration | Bucket | % complete | Priority | Depends on | Dependents (after) | Effort | Effort completed | Effort remaining | Milestone | Notes | Completed | Checklist Items | Labels | Sprint | Goal
1 | 1 | 0. JAKE DEDERT COACHING WEBSITE |  | 2025-07-09 09:00 | 2025-08-11 17:00 | 34 days |  | 0% | Medium | [5 empty] | No
2 | 1.1 | 1.0 Initiation |  | 2025-07-09 09:00 | 2025-07-10 17:00 | 2 days |  | 0% | Medium | [5 empty] | No
3 | 1.1.1 | Conduct initial client kickoff meeting |  | 2025-07-09 09:00 | 2025-07-09 17:00 | 1 day | Bucket 1 | 0% | Medium | [5 empty] | No |  |  |  |  | Backlog
4 | 1.1.2 | Create project proposal/charter |  | 2025-07-09 09:00 | 2025-07-09 17:00 | 1 day | Bucket 1 | 0% | Medium |  | 6FS |  |  |  | No |  |  |  |  | Backlog
5 | 1.1.3 | Set up project tools (MS Project, Jira, Teams, WordPress, Figma) |  | 2025-07-09 09:00 | 2025-07-10 17:00 | 2 days | Bucket 1 | 0% | Medium | [5 empty] | No |  |  |  |  | Backlog
6 | 1.1.4 | Present project proposal/charter with client |  | 2025-07-10 09:00 | 2025-07-10 17:00 | 1 day | Bucket 1 | 0% | Medium | 4FS | 7SS |  |  |  | No |  |  |  |  | Backlog
7 | 1.1.5 | Receive and implement project proposal/charter feedback |  | 2025-07-10 09:00 | 2025-07-10 17:00 | 1 day | Bucket 1 | 0% | Medium | 6SS | 8SS |  |  |  | No |  |  |  |  | Backlog
8 | 1.1.6 | Finalise and receive approval for project proposal/charter |  | 2025-07-10 09:00 | 2025-07-10 17:00 | 1 day | Bucket 1 | 0% | Medium | 7SS | 9FS |  |  |  | No |  |  |  |  | Backlog
9 | 1.1.7 | Milestone: Project Proposal/Charter approved |  | 2025-07-10 17:00 | 2025-07-10 17:00 | 0 days | Bucket 1 | 0% | Medium | 8FS | 12FS |  |  |  | Yes |  |  |  |  | Backlog
10 | 1.2 | 2.0 Analysis |  | 2025-07-14 09:00 | 2025-07-22 17:00 | 9 days |  | 0% | Medium | [5 empty] | No
11 | 1.2.1 | Requirements Gathering |  | 2025-07-14 09:00 | 2025-07-17 17:00 | 4 days |  | 0% | Medium | [5 empty] | No
12 | 1.2.1.1 | Conduct stakeholder interview (requirements elicitation) |  | 2025-07-14 09:00 | 2025-07-14 17:00 | 1 day | Bucket 1 | 0% | Medium | 9FS | 13FS |  |  |  | No |  |  |  |  | Backlog
13 | 1.2.1.2 | Develop user stories and feature list |  | 2025-07-15 09:00 | 2025-07-16 17:00 | 2 days | Bucket 1 | 0% | Medium | 12FS | 14FS |  |  |  | No |  |  |  |  | Backlog
14 | 1.2.1.3 | Prioritise features (MoSCoW) |  | 2025-07-17 09:00 | 2025-07-17 17:00 | 1 day | Bucket 1 | 0% | Medium | 13FS | 15SS |  |  |  | No |  |  |  |  | Backlog
15 | 1.2.1.4 | Present requirements document with client |  | 2025-07-17 09:00 | 2025-07-17 17:00 | 1 day | Bucket 1 | 0% | Medium | 14SS | 16SS |  |  |  | No |  |  |  |  | Backlog
16 | 1.2.1.5 | Adjust requirements document |  | 2025-07-17 09:00 | 2025-07-17 17:00 | 1 day | Bucket 1 | 0% | Medium | 15SS | 17SS |  |  |  | No |  |  |  |  | Backlog
17 | 1.2.1.6 | Finalise and receive approval for requirements document |  | 2025-07-17 09:00 | 2025-07-17 17:00 | 1 day | Bucket 1 | 0% | Medium | 16SS | 18FS |  |  |  | No |  |  |  |  | Backlog
18 | 1.2.1.7 | Milestone: Requirements gathering completed |  | 2025-07-17 17:00 | 2025-07-17 17:00 | 0 days | Bucket 1 | 0% | Medium | 17FS | 20FS |  |  |  | Yes |  |  |  |  | Backlog
19 | 1.2.2 | UI/UX Design (Prototypes) |  | 2025-07-18 09:00 | 2025-07-22 17:00 | 5 days |  | 0% | Medium | [5 empty] | No
20 | 1.2.2.1 | Create sitemap and information architecture |  | 2025-07-18 09:00 | 2025-07-18 17:00 | 1 day | Bucket 1 | 0% | Medium | 18FS | 21FS |  |  |  | No |  |  |  |  | Backlog
21 | 1.2.2.2 | Design desktop prototypes |  | 2025-07-19 09:00 | 2025-07-20 17:00 | 2 days | Bucket 1 | 0% | Medium | 20FS | 22SS, 23FS |  |  |  | No |  |  |  |  | Backlog
22 | 1.2.2.3 | Design mobile prototypes |  | 2025-07-19 09:00 | 2025-07-20 17:00 | 2 days | Bucket 1 | 0% | Medium | 21SS | 23FS |  |  |  | No |  |  |  |  | Backlog
23 | 1.2.2.4 | Simulate user flows |  | 2025-07-21 09:00 | 2025-07-21 17:00 | 1 day | Bucket 1 | 0% | Medium | 22FS, 21FS | 24FS |  |  |  | No |  |  |  |  | Backlog
24 | 1.2.2.5 | Share and collect feedback from client |  | 2025-07-22 09:00 | 2025-07-22 17:00 | 1 day | Bucket 1 | 0% | Medium | 23FS | 25SS, 26SS |  |  |  | No |  |  |  |  | Backlog
25 | 1.2.2.6 | Finalise and approve desktop prototypes |  | 2025-07-22 09:00 | 2025-07-22 17:00 | 1 day | Bucket 1 | 0% | Medium | 24SS | 27FS |  |  |  | No |  |  |  |  | Backlog
26 | 1.2.2.7 | Finalise and approve mobile prototypes |  | 2025-07-22 09:00 | 2025-07-22 17:00 | 1 day | Bucket 1 | 0% | Medium | 24SS | 27FS |  |  |  | No |  |  |  |  | Backlog
27 | 1.2.2.8 | Milestone: Prototypes approved |  | 2025-07-22 17:00 | 2025-07-22 17:00 | 0 days | Bucket 1 | 0% | Medium | 25FS, 26FS | 28SS |  |  |  | Yes |  |  |  |  | Backlog
28 | 1.2.2.9 | Milestone: Analysis phase completed |  | 2025-07-22 17:00 | 2025-07-22 17:00 | 0 days | Bucket 1 | 0% | Medium | 27SS | 30FS |  |  |  | Yes |  |  |  |  | Backlog
29 | 1.3 | 3.0 Implementation |  | 2025-07-23 09:00 | 2025-07-31 17:00 | 9 days |  | 0% | Medium | [5 empty] | No
30 | 1.3.1 | Sprint 1 Core Development (Homepage layout, about section, navigation elements) |  | 2025-07-23 09:00 | 2025-07-24 17:00 | 2 days | Bucket 1 | 0% | Medium | 28FS | 31FS |  |  |  | No |  |  |  |  | Backlog
31 | 1.3.2 | Sprint 1 Buffer (revisions and improvements upon client feedback) |  | 2025-07-25 09:00 | 2025-07-25 17:00 | 1 day | Bucket 1 | 0% | Medium | 30FS | 32FF |  |  |  | No |  |  |  |  | Backlog
32 | 1.3.3 | Milestone: Sprint 1 completed |  | 2025-07-25 17:00 | 2025-07-25 17:00 | 0 days | Bucket 1 | 0% | Medium | 31FF | 33FS |  |  |  | Yes |  |  |  |  | Backlog
33 | 1.3.4 | Sprint 2: Feature Development (Services page, Contact/Booking form) |  | 2025-07-26 09:00 | 2025-07-27 17:00 | 2 days | Bucket 1 | 0% | Medium | 32FS | 34FS |  |  |  | No |  |  |  |  | Backlog
34 | 1.3.5 | Sprint 2 Buffer (revisions and improvements upon client feedback) |  | 2025-07-28 09:00 | 2025-07-28 17:00 | 1 day | Bucket 1 | 0% | Medium | 33FS | 35FF |  |  |  | No |  |  |  |  | Backlog
35 | 1.3.6 | Milestone: Sprint 2 completed |  | 2025-07-28 17:00 | 2025-07-28 17:00 | 0 days | Bucket 1 | 0% | Medium | 34FF | 36FS |  |  |  | Yes |  |  |  |  | Backlog
36 | 1.3.7 | Sprint 3: Testing & Polish (Mobile fixes, QA, SEO) |  | 2025-07-29 09:00 | 2025-07-30 17:00 | 2 days | Bucket 1 | 0% | Medium | 35FS | 37FS |  |  |  | No |  |  |  |  | Backlog
37 | 1.3.8 | Sprint 3 Buffer (revisions and improvements upon client feedback) |  | 2025-07-31 09:00 | 2025-07-31 17:00 | 1 day | Bucket 1 | 0% | Medium | 36FS | 38FF |  |  |  | No |  |  |  |  | Backlog
38 | 1.3.9 | Milestone: Sprint 3 completed |  | 2025-07-31 17:00 | 2025-07-31 17:00 | 0 days | Bucket 1 | 0% | Medium | 37FF | 39FS |  |  |  | Yes |  |  |  |  | Backlog
39 | 1.3.10 | Milestone: Implementation phase completed |  | 2025-07-31 17:00 | 2025-07-31 17:00 | 0 days | Bucket 1 | 0% | Medium | 38FS | 41FS |  |  |  | Yes |  |  |  |  | Backlog
40 | 1.4 | 4.0 Deployment & Handover |  | 2025-08-01 09:00 | 2025-08-04 17:00 | 4 days |  | 0% | Medium | [5 empty] | No
41 | 1.4.1 | Deploy website to live domain/host |  | 2025-08-01 09:00 | 2025-08-01 17:00 | 1 day | Bucket 1 | 0% | Medium | 39FS | 42FS |  |  |  | No |  |  |  |  | Backlog
42 | 1.4.2 | Milestone: Project deployed |  | 2025-08-01 17:00 | 2025-08-01 17:00 | 0 days | Bucket 1 | 0% | Medium | 41FS | 43FS |  |  |  | Yes |  |  |  |  | Backlog
43 | 1.4.3 | Set up basic security, backup and SEO tools |  | 2025-08-02 09:00 | 2025-08-02 17:00 | 1 day | Bucket 1 | 0% | Medium | 42FS | 44FS |  |  |  | No |  |  |  |  | Backlog
44 | 1.4.4 | Conduct coach handover and walkthrough |  | 2025-08-03 09:00 | 2025-08-03 17:00 | 1 day | Bucket 1 | 0% | Medium | 43FS | 45FS |  |  |  | No |  |  |  |  | Backlog
45 | 1.4.5 | Milestone: Project handover completed |  | 2025-08-03 17:00 | 2025-08-03 17:00 | 0 days | Bucket 1 | 0% | Medium | 44FS | 46FS |  |  |  | Yes |  |  |  |  | Backlog
46 | 1.4.6 | Final project wrap up meeting |  | 2025-08-04 09:00 | 2025-08-04 17:00 | 1 day | Bucket 1 | 0% | Medium | 45FS | 47FS |  |  |  | No |  |  |  |  | Backlog
47 | 1.4.7 | Milestone: Project wrap up completed |  | 2025-08-04 17:00 | 2025-08-04 17:00 | 0 days | Bucket 1 | 0% | Medium | 46FS | 49FS |  |  |  | Yes |  |  |  |  | Backlog
48 | 1.5 | 5.0 Reflection & Portfolio Case Study |  | 2025-08-05 09:00 | 2025-08-11 17:00 | 7 days |  | 0% | Medium | [5 empty] | No
49 | 1.5.1 | Define user personas |  | 2025-08-05 09:00 | 2025-08-05 17:00 | 1 day | Bucket 1 | 0% | Medium | 47FS | 50FS |  |  |  | No |  |  |  |  | Backlog
50 | 1.5.2 | Conduct personal project retrospective |  | 2025-08-06 09:00 | 2025-08-07 17:00 | 2 days | Bucket 1 | 0% | Medium | 49FS | 51FS |  |  |  | No |  |  |  |  | Backlog
51 | 1.5.3 | Milestone: Personal retrospective complete |  | 2025-08-07 17:00 | 2025-08-07 17:00 | 0 days | Bucket 1 | 0% | Medium | 50FS | 52FS |  |  |  | Yes |  |  |  |  | Backlog
52 | 1.5.4 | Compile project screenshots and outcomes |  | 2025-08-08 09:00 | 2025-08-08 17:00 | 1 day | Bucket 1 | 0% | Medium | 51FS | 53SS |  |  |  | No |  |  |  |  | Backlog
53 | 1.5.5 | Write project case study for portfolio |  | 2025-08-08 09:00 | 2025-08-08 17:00 | 1 day | Bucket 1 | 0% | Medium | 52SS | 54FS |  |  |  | No |  |  |  |  | Backlog
54 | 1.5.6 | Publish documentation (Github, LinkedIn, Resume) |  | 2025-08-09 09:00 | 2025-08-11 17:00 | 3 days | Bucket 1 | 0% | Medium | 53FS | 55FS |  |  |  | No |  |  |  |  | Backlog
55 | 1.5.7 | Milestone: Project documentation published |  | 2025-08-11 17:00 | 2025-08-11 17:00 | 0 days | Bucket 1 | 0% | Medium | 54FS | 56FS |  |  |  | Yes |  |  |  |  | Backlog
56 | 1.5.8 | Milestone: Project closure/completion |  | 2025-08-11 17:00 | 2025-08-11 17:00 | 0 days | Bucket 1 | 0% | Medium | 55FS |  |  |  |  | Yes |  |  |  |  | Backlog